## Slide 1
Appendix G: Four-week validation plan with explicit scope cuts
Time
Milestone
Deliverable
Saria
Roxy
Aug. 7–13
Evidence
baseline
Freeze the schema-v8 demo; recruit 6–8 users; test opening → rescue → investigation → EchoLink; deliver success measures and a ranked issue log
Test build, event logging, bug triage, mobile and desktop fixes
Screener, recruitment, moderation, synthesis, presentation update
Aug. 14–20
Continuity and
trust refinement
Fix top usability issues; simplify memory and relationship language; verify source links, edit/delete, branch rewind, export/import; run a 5-user retest
State and storage fixes, accessibility, regression coverage
UX copy, prototype sessions, findings and prioritisation
Aug. 21–27
Constrained
live-AI spike
One-character server-side provider; offline fallback; scoped memory/context; timeout and error handling; side-by-side quality and safety review
Proxy, EchoEngine adapter, privacy and failure handling
Prompt and character QA, consent review, 5-user comparison
Aug. 28–
Sep. 3
Pilot and
hand-off
Run an 8-user pilot; resolve top P0/P1 issues; deliver the demo-ready build, research traceability, GitHub hand-off, final deck and next-step decision
Release QA, evidence instrumentation, technical hand-off, analytics summary
Pilot recruitment, evidence synthesis, final narrative and recommendations
Risk, fallback, and scope cuts
• No new characters, chapters, real calls/audio, notifications, community sharing, cloud accounts, native app, or infinite worlds.
• If live AI is unstable, unsafe, or late: keep the deterministic offline engine as default and ship the spike separately.
• If recruitment is slow: prioritise campus and friends-of-friends; reduce the Week 3 comparison before the final pilot.
• If continuity controls remain confusing: simplify labels and surface source/edit controls before adding more metrics.
Notes: [Sources]
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/PLANS.md
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/docs/PRODUCT_BRIEF.md
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/docs/RESEARCH_BASIS.md
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/docs/RESEARCH_TRACEABILITY.md
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/docs/ARCHITECTURE.md
- /Users/zihan/UofT/CSC454/EchoLoom_Interactive_Demo/docs/OPTIONAL_REAL_AI_UPGRADE.md
- npm test run on 2026-08-06: smoke suite PASS; schema-v8 state and engine suite PASS.
[/Sources]